## Introduction
Project Planning and Monitoring Tool
Purpose: This tool assists in organizing and monitoring project work. By using the task planning section, project milestones and tasks can accurately be planned out. Once the project begins, real-time progress is tracked and the project is monitored against the set baselines.
Instructions: This tool can be used for managing a project, starting with the planning stages right through to monitoring project progress. Refer to the boxes below to view each sections' instructions, and understand how each step is useful for managing projects. Alternatively, information entered in Microsoft Project can be copied and pasted into this tool to take advantage of its reporting capabilities. A simple copy and paste will work, however there is some preparation needed: 1. Ensure that the fields in MS Project are altered to match this tool. The order should be: Task Name, Start, Finish, and Resource Names. 2. Once pasted into this tool's Tab 2, reformat the start and finish columns to use a date format (within the Format menu, choose "Cells..." and select the desired date format). 3. Resource Names within MS Project must match the naming conventions used in this tool's Tab 1, table 1. Important Notice: Although this tool is capable of advanced functions, keep in mind that this is a light project management tool working within the limitations of Microsoft Excel. Pay close attention to any notices or warnings included within the individual tabs.
Getting Started: In chronological order, use the boxes below to navigate through the tool as the project progresses. Click the blue buttons to go directly to the section of choice, or use the worksheet tabs along the bottom of the spreadsheet screen. Some of the column headings in the sections include comments that offer additional instructions. Hover the mouse over the column headings to view these instructions.
| DATA ENTRY |  | PROJECT TASK PLANNING
| This section requires some basic data entry to get the project started. Information regarding project start and end dates, project team members and stakeholders, and non-work days is required. |  | Use this important section to plan out the project. Tasks should be entered, along with deadlines and task owners. Once hashed out and completed, copy and paste this plan into Tab 3 to begin monitoring project progress.
|  | Go to Data Entry |  | Go to Project Task Planning
| PROJECT MONITORING CHART |  | ISSUE LOG
| Copy and paste the project plan from Tab 2 into the first four columns of this Gantt chart. By entering the actual start and end dates for tasks, this chart allows you to view which tasks are on schedule, behind schedule or ahead of schedule. |  | If issues arise, use this area to log and ensure that problems are resolved.
|  | Go to Project Monitoring |  | Go to the Issue Log
CUSTOMIZED PROGRESS REPORT
Use this section to generate a custom progress report. Specify the time period that you would like to view and tasks during this time, ordered by task owner, will appear. This report is ideal for weekly meeting updates, or stakeholder progress reporting.
Go to Task Report
3
4
1
2
5

## 1. Data Entry
Basic Data Entry |  |  | Return to the Introduction
Fill in all of the white cells with the necessary information. To view additional instructions, hover your mouse over the table column headings.
Project Name | Pintos - User Programs
Estimated Project Start Date | 2018-09-08
Estimated Project End Date | 2018-10-13
Project Leader Name | Krisha Rain Martinez
1. Project Team Members, Task Groups & Stakeholders | 2. Holidays / Time Off Project
Name | Date | Holiday
Rain Martinez
Jericho Mamaradlo
Rod Labarete
Note on B14: List all project participants and stakeholders. Include all project member names that will be actually involved with owning/implementing parts of the project. Feel free to insert multiple names of a team.
Note on D14: All dates in this list will not be made available in the project planning gantt chart. Make sure that ranges are printed out one date at a time. For example, if there is a week of non-project work, print out the five days as separate entries. Make sure to include only days that are not dedicated to the project as a whole. Remember, these dates will be blanked out completely.

## 2. Planning
Planning |  | Return to the Introduction
Use this section to work out the project plan. Feel free to add and delete rows as necessary, or move tasks around until the optimal project plan has been drafted. Once satisfied with the project plan, copy this information and paste it into the corresponding table in Tab 3. No changes can be made to the project plan within Tab 3, so ensure that if any changes are needed, the adjustments are made in this tab before re-copying and re-pasting the data into Tab 3. An example has been included below.
Project Task Information
Project Task | Estimated Start Date | Estimated Completion Date | Task Owner (MUST USE DROP DOWN MENU)
implement argument passing | 2018-09-08 | 2018-09-21 | Jericho Mamaradlo
implement user memory access | 2018-09-08 | 2018-09-21 | Rod Labarete
implement system call infrastructure | 2018-09-08 | 2018-09-21 | Rain Martinez
test argument passing implementation | 2018-09-21 | 2018-09-26 | Rain Martinez
test user memory access implementation | 2018-09-21 | 2018-09-26 | Jericho Mamaradlo
test system call infastructure implementation | 2018-09-21 | 2018-09-26 | Rod Labarete
argument passing implementation changelog | 2018-09-25 | 2018-09-29 | Rain Martinez
user memory access implementation changelog | 2018-09-25 | 2018-09-29 | Jericho Mamaradlo
system call infastructure implementation changelog | 2018-09-25 | 2018-09-29 | Rod Labarete
implement exit system call | 2018-09-29 | 2018-10-06 | Jericho Mamaradlo
implement write system call | 2018-09-29 | 2018-10-06 | Rod Labarete
implement infinite loop for process_wait() | 2018-09-29 | 2018-10-06 | Rain Martinez
test exit system call implementation | 2018-10-06 | 2018-10-09 | Rain Martinez
test write system call implementation | 2018-10-06 | 2018-10-09 | Jericho Mamaradlo
test infinite process_wait() loop implementation | 2018-10-06 | 2018-10-09 | Rod Labarete
exit system call changelog implementation | 2018-10-08 | 2018-10-12 | Rain Martinez
write system call changelog implementation | 2018-10-08 | 2018-10-12 | Jericho Mamaradlo
infinite process_wait() loop changelog implementation | 2018-10-08 | 2018-10-12 | Rod Labarete
Note on E8: Use only the drop down menu to select the owner of the corresponding task. Groups of people, individuals, or departments can be used, depending on the entries made in the Data Entry section.

## 3. Task Monitoring
Work Schedule Monitoring | [11 empty] | Return to the Introduction
IMPORTANT NOTICE: It is very important that tasks are entered with unique names. If task names are repeated, the data will not carry over correctly. Make sure to name each task differently. IMPORTANT NOTICE: Rows cannot be inserted or deleted from the table below. If changes are made to the project plan, make these changes in Tab 2. Planning, and copy and paste the changes into this sheet. Be aware that the actual start and end dates will not update when changes are copy and pasted into this sheet, so make adjustments to these last two columns as necessary. | [6 empty] | GANTT CHART LEGEND
Holiday / Vacation / No Work
Planned Project Work Day
Task Completed
COMPLETION STATUS LEGEND
Task Completed Ahead of Schedule
Task Completed Behind Schedule
Project Task Information | [6 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25 |  |  |  |  | Week 26
Project Task | Estimated Start Date | Estimated Completion Date | Task Owner | Actual Start Date | Actual Completion Date | Comments | 2018-09-03 |  |  |  |  | 2018-09-10 |  |  |  |  | 2018-09-17 |  |  |  |  | 2018-09-24 |  |  |  |  | 2018-10-01 |  |  |  |  | 2018-10-08 |  |  |  |  | 2018-10-15 |  |  |  |  | 2018-10-22 |  |  |  |  | 2018-10-29 |  |  |  |  | 2018-11-05 |  |  |  |  | 2018-11-12 |  |  |  |  | 2018-11-19 |  |  |  |  | 2018-11-26 |  |  |  |  | 2018-12-03 |  |  |  |  | 2018-12-10 |  |  |  |  | 2018-12-17 |  |  |  |  | 2018-12-24 |  |  |  |  | 2018-12-31 |  |  |  |  | 2019-01-07 |  |  |  |  | 2019-01-14 |  |  |  |  | 2019-01-21 |  |  |  |  | 2019-01-28 |  |  |  |  | 2019-02-04 |  |  |  |  | 2019-02-11 |  |  |  |  | 2019-02-18 |  |  |  |  | 2019-02-25
[7 empty] | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 1
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
implement argument passing | 2018-09-08 | 2018-09-21 | Jericho Mamaradlo | 2018-09-08 | 2018-09-23 | bar: 2018-09-10 10 M to 2018-09-17 21 F
implement user memory access | 2018-09-08 | 2018-09-21 | Rod Labarete | 2018-09-08 | 2018-09-23 | bar: 2018-09-10 10 M to 2018-09-17 21 F
implement system call infrastructure | 2018-09-08 | 2018-09-21 | Rain Martinez | 2018-09-08 | 2018-09-23 | bar: 2018-09-10 10 M to 2018-09-17 21 F
test argument passing implementation | 2018-09-21 | 2018-09-26 | Rain Martinez | 2018-09-23 | bar: 2018-09-17 21 F to 2018-09-24 26 W
test user memory access implementation | 2018-09-21 | 2018-09-26 | Jericho Mamaradlo | 2018-09-23 | bar: 2018-09-17 21 F to 2018-09-24 26 W
test system call infastructure implementation | 2018-09-21 | 2018-09-26 | Rod Labarete | 2018-09-23 | bar: 2018-09-17 21 F to 2018-09-24 26 W
argument passing implementation changelog | 2018-09-25 | 2018-09-29 | Rain Martinez | 2018-09-24 | bar: 2018-09-24 25 T to 2018-09-24 28 F
user memory access implementation changelog | 2018-09-25 | 2018-09-29 | Jericho Mamaradlo | 2018-09-24 | bar: 2018-09-24 25 T to 2018-09-24 28 F
system call infastructure implementation changelog | 2018-09-25 | 2018-09-29 | Rod Labarete | 2018-09-24 | bar: 2018-09-24 25 T to 2018-09-24 28 F
implement exit system call | 2018-09-29 | 2018-10-06 | Jericho Mamaradlo | bar: 2018-10-01 1 M to 2018-10-01 5 F
implement write system call | 2018-09-29 | 2018-10-06 | Rod Labarete | bar: 2018-10-01 1 M to 2018-10-01 5 F
implement infinite loop for process_wait() | 2018-09-29 | 2018-10-06 | Rain Martinez | bar: 2018-10-01 1 M to 2018-10-01 5 F
test exit system call implementation | 2018-10-06 | 2018-10-09 | Rain Martinez | bar: 2018-10-08 8 M to 2018-10-08 9 T
test write system call implementation | 2018-10-06 | 2018-10-09 | Jericho Mamaradlo | bar: 2018-10-08 8 M to 2018-10-08 9 T
test infinite process_wait() loop implementation | 2018-10-06 | 2018-10-09 | Rod Labarete | bar: 2018-10-08 8 M to 2018-10-08 9 T
exit system call changelog implementation | 2018-10-08 | 2018-10-12 | Rain Martinez | bar: 2018-10-08 8 M to 2018-10-08 12 F
write system call changelog implementation | 2018-10-08 | 2018-10-12 | Jericho Mamaradlo | bar: 2018-10-08 8 M to 2018-10-08 12 F
infinite process_wait() loop changelog implementation | 2018-10-08 | 2018-10-12 | Rod Labarete | bar: 2018-10-08 8 M to 2018-10-08 12 F
Formulas:
Week 2 = [Week 1]+7
Week 3 = [Week 2]+7
Week 4 = [Week 3]+7
Week 5 = [Week 4]+7
Week 6 = [Week 5]+7
Week 7 = [Week 6]+7
Week 8 = [Week 7]+7
Week 9 = [Week 8]+7
Week 10 = [Week 9]+7
Week 11 = [Week 10]+7
Week 12 = [Week 11]+7
Week 13 = [Week 12]+7
Week 14 = [Week 13]+7
Week 15 = [Week 14]+7
Week 16 = [Week 15]+7
Week 17 = [Week 16]+7
Week 18 = [Week 17]+7
Week 19 = [Week 18]+7
Week 20 = [Week 19]+7
Week 21 = [Week 20]+7
Week 22 = [Week 21]+7
Week 23 = [Week 22]+7
Week 24 = [Week 23]+7
Week 25 = [Week 24]+7
Week 26 = [Week 25]+7
Note on B14: The first four columns of this table should be populated by copying and pasting the tasks that were planned out in Tab 2. The only new text that should be entered in this tab is the actual start and end dates.
Note on E14: Use ONLY the drop down menu to select the task owner name. Entering text that is not from the menu will result in reporting errors in Tab 4.
Note on H14: Insert task-specific comments as necessary. If useful, a hyperlink to a specific issue in Tab 4 can be created by hyperlinking within the document.

## 4. Issue Log
Issue Log |  |  | Return to the Introduction
Date | Issue | Comments | Resolution

## 5. Reporting
Customized Progress Report |  |  |  | Return to the Introduction
To create a customized progress report, insert the desired timeframe for analysis in the start and end date boxes below. For a progress report of the entire project, insert the project's start and end dates. Consider running reports based on tasks for today, this week, or next week. IMPORTANT NOTICE: Task owner names must be selected from the drop down menus in Tabs 2 and 3 in order for this reporting page to work correctly. If errors occur on this page, return to the project planning stage and ensure that task owner names were selected from the menus, rather than typed in manually.
Enter Date to Start Progress Report | 2018-09-08 | Enter Date to End Progress Report |  | 2018-10-13
Analysis of On-Schedule Tasks to Date | Analysis of Task Completion to Date |  | Analysis of Project Time Management
Task Owner | Task to be Completed During Specified Period | Task Status | Scheduled Due Date | On Track Status
Rain Martinez | test argument passing implementation | Task In Progress | 2018-09-26 | Task is scheduled for work during this timeframe.
| argument passing implementation changelog | Task In Progress | 2018-09-29 | Task is scheduled for work during this timeframe.
| implement infinite loop for process_wait() | Task Not Yet Started | 2018-10-06 | Task is scheduled for work during this timeframe.
| test exit system call implementation | Task Not Yet Started | 2018-10-09 | Task is scheduled for work during this timeframe.
| exit system call changelog implementation | Task Not Yet Started | 2018-10-12 | Task is scheduled for work during this timeframe.
Jericho Mamaradlo | test user memory access implementation | Task In Progress | 2018-09-26 | Task is scheduled for work during this timeframe.
| user memory access implementation changelog | Task In Progress | 2018-09-29 | Task is scheduled for work during this timeframe.
| implement exit system call | Task Not Yet Started | 2018-10-06 | Task is scheduled for work during this timeframe.
| test write system call implementation | Task Not Yet Started | 2018-10-09 | Task is scheduled for work during this timeframe.
| write system call changelog implementation | Task Not Yet Started | 2018-10-12 | Task is scheduled for work during this timeframe.
Rod Labarete | test system call infastructure implementation | Task In Progress | 2018-09-26 | Task is scheduled for work during this timeframe.
| system call infastructure implementation changelog | Task In Progress | 2018-09-29 | Task is scheduled for work during this timeframe.
| implement write system call | Task Not Yet Started | 2018-10-06 | Task is scheduled for work during this timeframe.
| test infinite process_wait() loop implementation | Task Not Yet Started | 2018-10-09 | Task is scheduled for work during this timeframe.
| infinite process_wait() loop changelog implementation | Task Not Yet Started | 2018-10-12 | Task is scheduled for work during this timeframe.

## Hidden (hidden)
| Variables> | "Stats" |  | Members | Date | Holiday Name
| actual | Not Yet Started | Team--> | Rain Martinez |  |  | Rain Martinez
| completion | In Progress |  | Jericho Mamaradlo |  |  | Jericho Mamaradlo
| status | Completed |  | Rod Labarete |  |  | Rod Labarete
Cancelled
| Status Var> | "Track"
Not Yet Started
| on track | Completed On Time
| completion | Completed Behind Schedule
| status | Completed Ahead of Schedule
In Progress
Cancelled
LINK PROJECT START DATE TO THE MONDAY BEFORE (For Gantt Chart)
[16 empty] | Which wkday is it? |  |  | Find what day it is | Convert it to Monday
[13 empty] | Start Date | 2018-09-08 |  | Saturday |  |  | Sunday
[13 empty] | The Monday | 2018-09-03 |  | Monday |  |  | Monday
Tuesday
Wednesday
Thursday
Friday
[19 empty] | Saturday | 43346
#For Tab 5 - Schedule Plan
#NO WORK HOLIDAY DATES
Week of | 2018-09-03 |  |  |  |  | 2018-09-10 |  |  |  |  | 2018-09-17 |  |  |  |  | 2018-09-24 |  |  |  |  | 2018-10-01 |  |  |  |  | 2018-10-08 |  |  |  |  | 2018-10-15 |  |  |  |  | 2018-10-22 |  |  |  |  | 2018-10-29 |  |  |  |  | 2018-11-05 |  |  |  |  | 2018-11-12 |  |  |  |  | 2018-11-19 |  |  |  |  | 2018-11-26 |  |  |  |  | 2018-12-03 |  |  |  |  | 2018-12-10 |  |  |  |  | 2018-12-17 |  |  |  |  | 2018-12-24 |  |  |  |  | 2018-12-31 |  |  |  |  | 2019-01-07 |  |  |  |  | 2019-01-14 |  |  |  |  | 2019-01-21 |  |  |  |  | 2019-01-28 |  |  |  |  | 2019-02-04 |  |  |  |  | 2019-02-11 |  |  |  |  | 2019-02-18 |  |  |  |  | 2019-02-25
Day Date | 43346 | 43347 | 43348 | 43349 | 43350 | 43353 | 43354 | 43355 | 43356 | 43357 | 43360 | 43361 | 43362 | 43363 | 43364 | 43367 | 43368 | 43369 | 43370 | 43371 | 43374 | 43375 | 43376 | 43377 | 43378 | 43381 | 43382 | 43383 | 43384 | 43385 | 43388 | 43389 | 43390 | 43391 | 43392 | 43395 | 43396 | 43397 | 43398 | 43399 | 43402 | 43403 | 43404 | 43405 | 43406 | 43409 | 43410 | 43411 | 43412 | 43413 | 43416 | 43417 | 43418 | 43419 | 43420 | 43423 | 43424 | 43425 | 43426 | 43427 | 43430 | 43431 | 43432 | 43433 | 43434 | 43437 | 43438 | 43439 | 43440 | 43441 | 43444 | 43445 | 43446 | 43447 | 43448 | 43451 | 43452 | 43453 | 43454 | 43455 | 43458 | 43459 | 43460 | 43461 | 43462 | 43465 | 43466 | 43467 | 43468 | 43469 | 43472 | 43473 | 43474 | 43475 | 43476 | 43479 | 43480 | 43481 | 43482 | 43483 | 43486 | 43487 | 43488 | 43489 | 43490 | 43493 | 43494 | 43495 | 43496 | 43497 | 43500 | 43501 | 43502 | 43503 | 43504 | 43507 | 43508 | 43509 | 43510 | 43511 | 43514 | 43515 | 43516 | 43517 | 43518 | 43521 | 43522 | 43523 | 43524 | 43525
HOLIDAY? | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No
|  | SUM: | [5 empty] | For Pie chart 2 in Today's View - TOTAL PROJECT |  |  |  | For Pie chart 1 in Today - Today's Tasks |  |  |  | For Time Line in Today |  |  | Not subtracting weekends & holidays… | [6 empty] | Task is underway but is behind schedule.
|  | #REF! |  | Today | 2018-09-24 | CODE TASKS FOR THIS WEEK…. Ugh/ |  | Tasks Completed | 16.67% |  |  | Behind Schedule Tasks - Started | 0 |  |  | Project Start | 43351 |  | Project Days Passed | 16 | 45.71% |  |  |  |  | Task is late and has not yet been started.
[8 empty] | Tasks In Progress | 33.33% |  |  | Behind Schedule Tasks - Not Yet Started | 0 |  |  | Today | 43367 |  | Project Days Left | 19 | 54.29%
|  | AMOUNT | [5 empty] | Tasks Not Yet Started | 50% |  |  | Regularly Scheduled Tasks | 1 |  |  | Project End | 43386
|  | 15 |  |  | Total tasks | 18 | [5 empty] | QC | 1 | [5 empty] | QC | 35
[8 empty] | QC | 100% | [10 empty] | 35
Note on N30: From user input
Note on N31: The Monday of the first week of project commencement...

## HiddenWkly (hidden)
"Weekly" (or whatever) task view | [10 empty] | Task Not Yet Started |  |  | Task is underway but is behind schedule.
[11 empty] | Task Complete |  |  | Task is late and has not yet been started.
start date entry | 2018-09-08 | [9 empty] | Task In Progress |  |  | Task is scheduled for work during this timeframe.
End date entry | 2018-10-13
[26 empty] | TO ORDER BY TASK OWNER |  |  |  |  | Actual list for Tab
TASK NUMBER | ID for Task | "Rank" to list | Repeat Task for VLOOKUP | TASK | Estimated Start Date | Estimated End Date | Owner | Owner for List | Actual Start Date | Actual End Date |  | On Track Status | Task should be done - Started | Task Should be done - Not Yet Started | Reg Scheduled Task during this time | Sum | Unique Rank for Owners, by task | Owner Rank | Task Owner | List of tasks | Task Name | Est Start Date | Est End Date - DUE DATE | Completion Status | On Track Status | Possible Owner | Task Number | Yes to tasks | Unique Rank |  | RANK | Owner | Owner for Tab | Task | Task Status | Due Date | Completion Status
1 | [14 empty] | No | 1 | 1 | 1 | Rain Martinez | 1 | test argument passing implementation | 43364 | 43369 | Task In Progress | Task is scheduled for work during this timeframe. | Unassigned | 0 |  |  | Rain Martinez | 1 | Rain Martinez | Rain Martinez | test argument passing implementation | Task In Progress | 2018-09-26 | Task is scheduled for work during this timeframe.
2 |  |  |  | implement argument passing | 43351 | 43364 | Jericho Mamaradlo | Jericho Mamaradlo | 2018-09-08 | 2018-09-23 | Task Complete |  | No | No | No | 3 | 6 | 2 | Jericho Mamaradlo | 2 | test user memory access implementation | 43364 | 43369 | Task In Progress | Task is scheduled for work during this timeframe. | Rain Martinez | 5 | 5 | 1 | Jericho Mamaradlo | 2 | Rain Martinez |  | argument passing implementation changelog | Task In Progress | 2018-09-29 | Task is scheduled for work during this timeframe.
3 |  |  |  | implement user memory access | 43351 | 43364 | Rod Labarete | Rod Labarete | 2018-09-08 | 2018-09-23 | Task Complete |  | No | No | No | 6 | 11 | 3 | Rod Labarete | 3 | test system call infastructure implementation | 43364 | 43369 | Task In Progress | Task is scheduled for work during this timeframe. | Jericho Mamaradlo | 5 | 5 | 2 | Rod Labarete | 3 | Rain Martinez |  | implement infinite loop for process_wait() | Task Not Yet Started | 2018-10-06 | Task is scheduled for work during this timeframe.
4 |  |  |  | implement system call infrastructure | 43351 | 43364 | Rain Martinez | Rain Martinez | 2018-09-08 | 2018-09-23 | Task Complete |  | No | No | No | 10 | 2 | 1 | Rain Martinez | 4 | argument passing implementation changelog | 43368 | 43372 | Task In Progress | Task is scheduled for work during this timeframe. | Rod Labarete | 5 | 5 | 3 | 0 | 4 | Rain Martinez |  | test exit system call implementation | Task Not Yet Started | 2018-10-09 | Task is scheduled for work during this timeframe.
5 | [14 empty] | No | 15 | 7 | 2 | Jericho Mamaradlo | 5 | user memory access implementation changelog | 43368 | 43372 | Task In Progress | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 5 | Rain Martinez |  | exit system call changelog implementation | Task Not Yet Started | 2018-10-12 | Task is scheduled for work during this timeframe.
6 | 6 | 1 | test argument passing implementation | test argument passing implementation | 43364 | 43369 | Rain Martinez | Rain Martinez | 2018-09-23 |  | Task In Progress | Task is scheduled for work during this timeframe. | No | No | Yes | 21 | 12 | 3 | Rod Labarete | 6 | system call infastructure implementation changelog | 43368 | 43372 | Task In Progress | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 6 | Jericho Mamaradlo | Jericho Mamaradlo | test user memory access implementation | Task In Progress | 2018-09-26 | Task is scheduled for work during this timeframe.
7 | 7 | 2 | test user memory access implementation | test user memory access implementation | 43364 | 43369 | Jericho Mamaradlo | Jericho Mamaradlo | 2018-09-23 |  | Task In Progress | Task is scheduled for work during this timeframe. | No | No | Yes | 28 | 8 | 2 | Jericho Mamaradlo | 7 | implement exit system call | 43372 | 43379 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 7 | Jericho Mamaradlo |  | user memory access implementation changelog | Task In Progress | 2018-09-29 | Task is scheduled for work during this timeframe.
8 | 8 | 3 | test system call infastructure implementation | test system call infastructure implementation | 43364 | 43369 | Rod Labarete | Rod Labarete | 2018-09-23 |  | Task In Progress | Task is scheduled for work during this timeframe. | No | No | Yes | 36 | 13 | 3 | Rod Labarete | 8 | implement write system call | 43372 | 43379 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 8 | Jericho Mamaradlo |  | implement exit system call | Task Not Yet Started | 2018-10-06 | Task is scheduled for work during this timeframe.
9 | [14 empty] | No | 45 | 3 | 1 | Rain Martinez | 9 | implement infinite loop for process_wait() | 43372 | 43379 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 9 | Jericho Mamaradlo |  | test write system call implementation | Task Not Yet Started | 2018-10-09 | Task is scheduled for work during this timeframe.
10 | 10 | 4 | argument passing implementation changelog | argument passing implementation changelog | 43368 | 43372 | Rain Martinez | Rain Martinez | 2018-09-24 |  | Task In Progress | Task is scheduled for work during this timeframe. | No | No | Yes | 55 | 4 | 1 | Rain Martinez | 10 | test exit system call implementation | 43379 | 43382 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 10 | Jericho Mamaradlo |  | write system call changelog implementation | Task Not Yet Started | 2018-10-12 | Task is scheduled for work during this timeframe.
11 | 11 | 5 | user memory access implementation changelog | user memory access implementation changelog | 43368 | 43372 | Jericho Mamaradlo | Jericho Mamaradlo | 2018-09-24 |  | Task In Progress | Task is scheduled for work during this timeframe. | No | No | Yes | 66 | 9 | 2 | Jericho Mamaradlo | 11 | test write system call implementation | 43379 | 43382 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 11 | Rod Labarete | Rod Labarete | test system call infastructure implementation | Task In Progress | 2018-09-26 | Task is scheduled for work during this timeframe.
12 | 12 | 6 | system call infastructure implementation changelog | system call infastructure implementation changelog | 43368 | 43372 | Rod Labarete | Rod Labarete | 2018-09-24 |  | Task In Progress | Task is scheduled for work during this timeframe. | No | No | Yes | 78 | 14 | 3 | Rod Labarete | 12 | test infinite process_wait() loop implementation | 43379 | 43382 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 12 | Rod Labarete |  | system call infastructure implementation changelog | Task In Progress | 2018-09-29 | Task is scheduled for work during this timeframe.
13 | [14 empty] | No | 91 | 5 | 1 | Rain Martinez | 13 | exit system call changelog implementation | 43381 | 43385 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 13 | Rod Labarete |  | implement write system call | Task Not Yet Started | 2018-10-06 | Task is scheduled for work during this timeframe.
14 | 14 | 7 | implement exit system call | implement exit system call | 43372 | 43379 | Jericho Mamaradlo | Jericho Mamaradlo |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 105 | 10 | 2 | Jericho Mamaradlo | 14 | write system call changelog implementation | 43381 | 43385 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 14 | Rod Labarete |  | test infinite process_wait() loop implementation | Task Not Yet Started | 2018-10-09 | Task is scheduled for work during this timeframe.
15 | 15 | 8 | implement write system call | implement write system call | 43372 | 43379 | Rod Labarete | Rod Labarete |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 120 | 15 | 3 | Rod Labarete | 15 | infinite process_wait() loop changelog implementation | 43381 | 43385 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 15 | Rod Labarete |  | infinite process_wait() loop changelog implementation | Task Not Yet Started | 2018-10-12 | Task is scheduled for work during this timeframe.
16 | 16 | 9 | implement infinite loop for process_wait() | implement infinite loop for process_wait() | 43372 | 43379 | Rain Martinez | Rain Martinez |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 136 | [9 empty] | 0 |  |  |  | 0 | 16
17 | [14 empty] | No | 153 | [9 empty] | 0 |  |  |  | 0 | 17
18 | 18 | 10 | test exit system call implementation | test exit system call implementation | 43379 | 43382 | Rain Martinez | Rain Martinez |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 171 | [9 empty] | 0 |  |  |  | 0 | 18
19 | 19 | 11 | test write system call implementation | test write system call implementation | 43379 | 43382 | Jericho Mamaradlo | Jericho Mamaradlo |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 190 | [9 empty] | 0 |  |  |  | 0 | 19
20 | 20 | 12 | test infinite process_wait() loop implementation | test infinite process_wait() loop implementation | 43379 | 43382 | Rod Labarete | Rod Labarete |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 210 | [9 empty] | 0 |  |  |  | 0 | 20
21 | [14 empty] | No | 231 | [9 empty] | 0 |  |  |  | 0 | 21
22 | 22 | 13 | exit system call changelog implementation | exit system call changelog implementation | 43381 | 43385 | Rain Martinez | Rain Martinez |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 253 | [9 empty] | 0 |  |  |  | 0 | 22
23 | 23 | 14 | write system call changelog implementation | write system call changelog implementation | 43381 | 43385 | Jericho Mamaradlo | Jericho Mamaradlo |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 276 | [9 empty] | 0 |  |  |  | 0 | 23
24 | 24 | 15 | infinite process_wait() loop changelog implementation | infinite process_wait() loop changelog implementation | 43381 | 43385 | Rod Labarete | Rod Labarete |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 300 | [9 empty] | 0 |  |  |  | 0 | 24
25 | [14 empty] | No | 325 | [9 empty] | 0 |  |  |  | 0 | 25
26 | [14 empty] | No | 351 | [9 empty] | 0 |  |  |  | 0 | 26
27 | [14 empty] | No | 378 | [9 empty] | 0 |  |  |  | 0 | 27
28 | [14 empty] | No | 406 | [9 empty] | 0 |  |  |  | 0 | 28
29 | [14 empty] | No | 435 | [9 empty] | 0 |  |  |  | 0 | 29
30 | [14 empty] | No | 465 | [9 empty] | 0 |  |  |  | 0 | 30
31 | [14 empty] | No | 496 | [9 empty] | 0 |  |  |  | 0 | 31
32 | [14 empty] | No | 528 | [9 empty] | 0 |  |  |  | 0 | 32
33 | [14 empty] | No | 561 | [9 empty] | 0 |  |  |  | 0 | 33
34 | [14 empty] | No | 595 | [9 empty] | 0 |  |  |  | 0 | 34
35 | [14 empty] | No | 630 | [9 empty] | 0 |  |  |  | 0 | 35
36 | [14 empty] | No | 666 | [9 empty] | 0 |  |  |  | 0 | 36
37 | [14 empty] | No | 703 | [9 empty] | 0 |  |  |  | 0 | 37
38 | [14 empty] | No | 741 | [9 empty] | 0 |  |  |  | 0 | 38
39 | [14 empty] | No | 780 | [9 empty] | 0 |  |  |  | 0 | 39
40 | [14 empty] | No | 820 | [9 empty] | 0 |  |  |  | 0 | 40
41 | [14 empty] | No | 861 | [9 empty] | 0 |  |  |  | 0 | 41
42 | [14 empty] | No | 903 | [14 empty] | 42
43 | [14 empty] | No | 946 | [14 empty] | 43
44 | [14 empty] | No | 990 | [14 empty] | 44
45 | [14 empty] | No | 1035 | [14 empty] | 45
46 | [14 empty] | No | 1081 | [14 empty] | 46
47 | [14 empty] | No | 1128 | [14 empty] | 47
48 | [14 empty] | No | 1176 | [14 empty] | 48
49 | [14 empty] | No | 1225 | [14 empty] | 49
50 | [14 empty] | No | 1275 | [14 empty] | 50
51 | [14 empty] | No | 1326 | [14 empty] | 51
52 | [14 empty] | No | 1378 | [14 empty] | 52
53 | [14 empty] | No | 1431 | [14 empty] | 53
54 | [14 empty] | No | 1485 | [14 empty] | 54
55 | [14 empty] | No | 1540 | [14 empty] | 55
56 | [14 empty] | No | 1596 | [14 empty] | 56
57 | [14 empty] | No | 1653 | [14 empty] | 57
58 | [14 empty] | No | 1711 | [14 empty] | 58
59 | [14 empty] | No | 1770 | [14 empty] | 59
60 | [14 empty] | No | 1830 | [14 empty] | 60
61 | [14 empty] | No | 1891 | [14 empty] | 61
62 | [14 empty] | No | 1953 | [14 empty] | 62
63 | [14 empty] | No | 2016 | [14 empty] | 63
64 | [14 empty] | No | 2080 | [14 empty] | 64
65 | [14 empty] | No | 2145 | [14 empty] | 65
66 | [14 empty] | No | 2211 | [14 empty] | 66
67 | [14 empty] | No | 2278 | [14 empty] | 67
68 | [14 empty] | No | 2346 | [14 empty] | 68
69 | [14 empty] | No | 2415 | [14 empty] | 69
70 | [14 empty] | No | 2485 | [14 empty] | 70
71 | [14 empty] | No | 2556 | [14 empty] | 71
72 | [14 empty] | No | 2628 | [14 empty] | 72
73 | [14 empty] | No | 2701 | [14 empty] | 73
74 | [14 empty] | No | 2775 | [14 empty] | 74
75 | [14 empty] | No | 2850 | [14 empty] | 75
76 | [14 empty] | No | 2926 | [14 empty] | 76
77 | [14 empty] | No | 3003 | [14 empty] | 77
78 | [14 empty] | No | 3081 | [14 empty] | 78
79 | [14 empty] | No | 3160 | [14 empty] | 79
80 | [14 empty] | No | 3240 | [14 empty] | 80
81 | [14 empty] | No | 3321 | [14 empty] | 81
82 | [14 empty] | No | 3403 | [14 empty] | 82
83 | [14 empty] | No | 3486 | [14 empty] | 83
84 | [14 empty] | No | 3570 | [14 empty] | 84
85 | [14 empty] | No | 3655 | [14 empty] | 85
86 | [14 empty] | No | 3741 | [14 empty] | 86
87 | [14 empty] | No | 3828 | [14 empty] | 87
88 | [14 empty] | No | 3916 | [14 empty] | 88
89 | [14 empty] | No | 4005 | [14 empty] | 89
90 | [14 empty] | No | 4095 | [14 empty] | 90
91 | [14 empty] | No | 4186 | [14 empty] | 91
92 | [14 empty] | No | 4278 | [14 empty] | 92
93 | [14 empty] | No | 4371 | [14 empty] | 93
94 | [14 empty] | No | 4465 | [14 empty] | 94
95 | [14 empty] | No | 4560 | [14 empty] | 95
96 | [14 empty] | No | 4656 | [14 empty] | 96
97 | [14 empty] | No | 4753 | [14 empty] | 97
98 | [14 empty] | No | 4851 | [14 empty] | 98
99 | [14 empty] | No | 4950 | [14 empty] | 99
100 | [14 empty] | No | 5050 | [14 empty] | 100
Formulas:
Due Date = IF(SUM(S10:S109)<[Sum],"",VLOOKUP([RANK],S10:AA109,7,FALSE))

## Compatibility Report
Compatibility Report for Project_Scheduling_and_Monitoring_Tool.xls
Run on 2/15/2018 10:39
If the workbook is saved in an earlier file format or opened in an earlier version of Microsoft Excel, the listed features will not be available.
Significant loss of functionality | # of occurrences | Version
Any effects on this object will be removed. Any text that overflows the boundaries of this graphic will appear truncated. | 5
| Introduction'!B4:W182 | Excel 97-2003
Some cells in this workbook contain data validation rules, which refer to values on other worksheets. These rules won't be saved. | 5
| 3. Task Monitoring'!G30:H30 | Excel 97-2003
3. Task Monitoring'!G32:H34
3. Task Monitoring'!D17:D22
3. Task Monitoring'!D24:D116
| 5. Reporting'!H6:H7 | Excel 97-2003
Minor loss of fidelity
Some formulas in this workbook are linked to other workbooks that are closed. When these formulas are recalculated in earlier versions of Excel without opening the linked workbooks, characters beyond the 255-character limit cannot be returned. | 2 Defined Names | Excel 97-2003